## Environmental Part
Package_WD_06 Summary (Environmental Part)
General Information | [5 empty] | B1 Environmental Features | [7 empty] | B2 Pre Construction Phase |  |  |  |  | B3 Construction Phase | [8 empty] | B4 Operation Phase | [7 empty] | Section_D Impact Summary (Sub-project interventions) |  |  | Section_D Impact Summary (Pre-construction Phase) |  |  | Section_D Impact Summary (Construction Phase) | [7 empty] | Section_D Impact Summary (Operational Phase)
Sl.No | Package ID_06 | Lat | Long | Camp | Block | Landslide potential | Wildlife Issue | Forest Issue | Existing drainage channel (Rivers, canals) Issue with distance (feet) | Sensitive Reciptor (Archologicak, Cultural site, etc.) | Livelihood Issues | Access Road | Approx. Area Required (sqm) | Stagnant Water Risk | Existing drinage channel (Rivers, canels) Issue | Aquatic ecosystems Issue | Storage of construction materials issue | Triffic movement Issue | Construction Waste (drillinng Mud, etc.) | Stagnant Water Issue | Storage of Materilals | Existing drinage channel (Rivers, canels) Issue | Aquatic ecosystems Issue | Land Erosion Issue | Triffic movement Issue | Sensitive Reciptor (Archologicak, Cultural site, etc.) | Employment (positive impact) | Health Hazards Issue (Fecal Sludge & Liquid waste) | Destruction soils Issue | Odor, water & soil quality impacts Issure | Stagnant Water Risk | Improvement of quality of livelihood | Existing drinage channel (Rivers, canels) Issue | Aquatic ecosystems Issue | Triffic movement Issue | Air Quality Impact | Soil Impcat | Hydrology (SW & GW) Impact | Sanitation, water sypply Impact | Storage of construction materials Impact | Transportation Impact | Wastes (Drilling mud, etc.) Impact | Stagnant Water Issue | Storage of Materilals Impact | Impact on Drainage & Aquatic Environment | Erosion of land Impact | Noise Pollution Impact | Air Pollution Impact | Generation of Employment (+) | Health & Safety Hazard | Destruction of Soil Impact | Odor & waste disposal Impact | Stagnant Water Risk | Improvement of quality of livelihood (+ve) | Impact on Drainage & Aquatic Environment | Noise Pollution Impact | Air Pollution Impact
1 | EMCRP-WD-06 | 21.2136 | 92.1568 | Camp 1E | F | Low | No | No | No | Madrasha | Yes | Yes | 40 | None | Low (negligible) | Low (negligible) | Yes | Yes | Yes | Medium | Yes | None | Medium | Medium | Yes | Madrasha | Yes | Yes | Low | Medium | Low | Yes | None | Medium | Yes | Low | Low | Low | Low | Low | Low | Medium | Medium | Medium | Medium | Medium | Medium | Low | Low to Medium | Low | Low | Medium | Low | Medium | Medium | Low | Low
2 |  | 21.2136 | 92.1568 |  | F | Low | No | No | No | Madrasha | Yes | Yes | 40 | None | Low (negligible) | Low (negligible) | Yes | Yes | Yes | Medium | Yes | None | Medium | Medium | Yes | Madrasha | Yes | Yes | Low | Medium | Low | Yes | None | Medium | Yes | Low | Low | Low | Low | Low | Low | Medium | Medium | Medium | Medium | Medium | Medium | Low | Low to Medium | Low | Low | Medium | Low | Medium | Medium | Low | Low
3 |  | 21.2136 | 92.1566 |  | F | Low | No | No | No | Madrasha & Mosque | Yes | Yes | 40 | None | Low (negligible) | Low (negligible) | Yes | Yes | Yes | Medium | Yes | None | Medium | Medium | Yes | Madrasha & Mosque | Yes | Yes | Low | Medium | Low | Yes | None | Medium | Yes | Low | Low | Low | Low | Low | Low | Medium | Medium | Medium | Medium | Medium | Medium | Low | Low to Medium | Low | Low | Medium | Low | Medium | Medium | Low | Low
4 |  | 21.2136 | 92.1566 |  | F | Low | No | No | No | Madrasha & Mosque | Yes | Yes | 40 | None | Low (negligible) | Low (negligible) | Yes | Yes | Yes | Medium | Yes | None | Medium | Medium | Yes | Madrasha & Mosque | Yes | Yes | Low | Medium | Low | Yes | None | Medium | Yes | Low | Low | Low | Low | Low | Low | Medium | Medium | Medium | Medium | Medium | Medium | Low | Low to Medium | Low | Low | Medium | Low | Medium | Medium | Low | Low

## Social & Gender Part
Package_WD_06 Summary (Social Part)
Sl No. | Lat | Long | Camp | Block | Will the project potentially involve an influx of workers to the project location, and will the influx be considered significant for the local community? | Is the project located in a rural or remote area? | Section C1, General Labor Influx Screening and Labor and Contractors management during COVID-19 | Section C2, Land acquisition and stakeholder screening and Labor and Contractors management during COVID-19 | Section C3, Social Capital Format | Photograph
1 | 21.2136 | 92.1568 | Camp-1E | F | Under the, subproject community latrine at DRP area, as per the E&S Safeguard team labor influx is not a significant issue at DRP subproject areas. Total skilled Labor: 2-3, unskilled labor 3-5 need per community latrine construction. All the unskilled labor will be engaged by the DRP community. No foreign labor will be engaged. All the skilled labor will stay at labor shed within the camp. The size of the labor shed will 225 s. feet for male and 180 sq. feet (need based) for the female. The frequency and extent of contact, communicate between the local community and outsiders are limited and controlled by the respective SMC and CiC management. Noted that the incoming workers will be very low in numbers, so there will be no competition to use those resources. And, during screening and site identification process the CiC & local DPHE, the assigned consultants have conducted 2 (two) Consultation meetings for four community latrines. Other than the mentioned meetings, the local DPHE has conducted many other consultation with DRP male and females. By the effort of coordination and linkage activities of project authority accomplished some formal view exchange meeting, individual household visit, FGD, Tea stall discussion, consultation meetings. Local people will not be allowed to visit camp without the permission of CiC. The frequency and extent of contact, communicate between the local community and outsiders are limited and controlled by the respective SMC and CiC. Also noted that UNFPA is being hired as a specialized organization to deal with the GBV activities. This project is a part of the Gender Component of the UNFPA 9th Country Program and will contribute to achieve the CP outcome 3 ‘‘Advanced gender equality, women’s and girls’ empowerment, and reproductive rights, including for the most vulnerable and marginalized women, adolescents and youth’’. | Yes, obviously the sub-project Community Latrine construction and O&M located in a remote hilly, corrugated CiC assigned DRP Camp area. The frequency and extent of contact, communicate between the local community and outsiders are limited and controlled by the respective CIC. The area isn’t sensitive at environmental conditions. BRAC is acting as WASH camp focal agency, UNHCR is acting area focal agency of the area DPHE is implementing the project with the financial assistance of World Bank and Govt. of Bangladesh. By establishing the community latrine scheme, about 80-85 people will be benefitted. In the Camp 1E around 37,690 people over there. Within the community latrine are as CiC office, health post, mosques, madrasha, graveyard, food distribution centers and information centers is identified. However, none is going to be affected due to project intervention. No disturbance is anticipated due to construction activities to those environmental and social components. In this scheme area, no elephant migration routes exists (ref. IUCN). The DRP will be benefited from the sub-project. | Regarding General Labor Influx screening process under the sub-project ( DRP Community Latrine) establishment in the proposed areas , it has been revealed that no scope to arise labor influx situation. Total skilled Labor: 2-3, unskilled labor 3-5 need per Latrine installation. All of the unskilled labor will be engaged from the DRP community. No foreign labor will be engaged. To establish the scheme tasks, some outsider labor and technicians will be engaged over there; so scope to arise social conflict might be raised. A complete Gender action plan already developed and approved, a full time Gender Specialist of this project has been assigned to oversee the GBV based issues for this subproject. The gender and gender-based violence issues (i.e. human trafficking, eve teasing, etc.) are being addressed through mainstreaming activities. As the mitigation measure the Social Safeguard team and GRC has been following the respective GRM, will aware on GBV and motivate the community through consultation meeting, counseling. Given the sensitivities in the camps areas (social, cultural, religious, gender, disabilities, orphan. No DRP shelters will be affected. However, during construction if any shelters require to shift, mitigation measures will be taken according to RPF. Consultations will be conducted with stakeholders, camp and block focal persons and site management. During construction, if any shelters are affected, contractors are responsible to mitigate the impacts following the RPF as well. Labor and Contractors management during COVID-19 : For projects involving construction/ civil works, contractors will develop specific procedures or plans so that adequate precautions are in place to prevent or minimize an outbreak of COVID-19, and what should be done if a worker gets sick.: • DPHE has oriented the contractor and labor on Covid-19 management including OHS (Occupational Health Safety). • Assessing the characteristics of the workforce, including those with underlying health issues or who may be otherwise at risk • Confirming workers are fit for work, to include temperature testing and refusing entry to sick workers • Considering ways to minimize entry/exit to site or the workplace, and limiting contact between workers and the community/general public • Training workers on hygiene and other preventative measures, and implementing a communication strategy for regular updates on COVID-19 related issues and the status of affected workers • Treatment of workers who are or should be self-isolating and/or are displaying symptoms • Assessing risks to continuity of supplies of medicine, water, fuel, food and PPE, taking into account international, national and local supply chains • Reduction, storage and disposal of medical waste • Adjustments to work practices, to reduce the number of workers and increase social distancing • Expanding health facilities on-site compared to usual levels, developing relationships with local health care facilities and organize for the treatment of sick workers • Building worker accommodations further apart, or having one worker accommodation in a more isolated area, which may be easily converted to quarantine and treatment facilities, if needed • Establishing a procedure to follow if a worker becomes sick (following WHO guidelines) • Implementing a communication strategy with the community, community leaders and local government in relation to COVID-19 issues on the site. For supporting health facilities, plans or procedures will be in place to address the following issues: • Obtaining adequate supplies of medical PPE, including gowns, aprons, curtains; medical masks and respirators (N95 or FFP2); gloves (medical, and heavy duty for cleaners); eye protection (goggles or face screens); hand washing soap and sanitizer; and effective cleaning equipment. Where relevant PPE cannot be obtained, the plan should consider viable alternatives, such as cloth masks, alcohol-based cleansers, hot water for cleaning and extra handwashing facilities, until such time as the supplies are available • Training medical staff on the latest WHO advice and recommendations on the specifics of COVID-19 • Conducting enhanced cleaning arrangements, including thorough cleaning (using adequate disinfectant) of catering facilities/canteens/food/drink facilities, latrines/toilets/showers, common areas, including door handles, floors and all surfaces that are touched regularly. | No, land acquisition is not for this subproject community latrine establishment at the proposed DRP Camp-1E site. The ownership of the land is government and lands are currently empty. The land is selected with the recommendation of CiC, SMC & Local DPHE and assigned UN agencies. The DRP Tent and their Shelter will not be affected or shifted due to the sub project activities. If the tents of the DRP be affected if any, appropriate mitigation measures (as per ESMF-RAP-GRM) would be taken place, as well as adequate consultation with the DRP and SHs. In the consultation session elaborately discussed on environmental and social aspects of project interventions. It is noted that any agro, non-agro establishments, assets, habitat would not be displaced by this subproject interventions. So that there is no possibility of unrest - conflict situation to be raised. The community and elites were very much welcomed, praised appreciated the DPHE-EMCRP initiatives on WASH sector sub projects. As per their opinion, the safe water and improved sanitation (Latrine construction) is one of the priority needs for them for secured and better livelihoods aspects. They opined that it is not an Elephant corridor and no scope of Elephant/ Human conflict. By the consultation meeting, the participants from DRP community become aware and sensitized on E&S probable impact issues, precautions, child safety etc. Team sincerely briefed the role of DRP to-do & not to-do, compensation mechanism if any objection and complaints. | Aiming to seek necessary support to accomplish community latrine scheme In the Camp-1E in the E&S Screening Process we have listed down the concerned social institutes/bodies working in the camp, intended project influence areas to enlist them for the possible inclusion in the management and monitoring of the projects. List the name of social institutes/ bodies under the given categorization along with the following information. Use separate sheet for each category of social institute/ body. The information can be collected through secondary sources such as RRRC/UN agencies or different development organizations that are involved with the DRP crisis projects, i.e. -Bangladesh Government agencies - Mr. Shah Rezwan Hayat, RRRC Commissioner, CXB, Email rrccox@yahoo.com …………………………………….. Engr. Ritthick Chowdhury, DPHE, Executive Engineer, CXB, Email. chowritthick@gmail.com Md. Mamunur Rashid dccoxsbazar@mopa.gov.bd Mr. Anupam Das Anup Camp-in-Charge, Camp-1E (Assistant Secretary) Camp1e@rrrc.gov.bd Emmett Kearney Area Focal Agency, UNHCR KearneyE@unhcr.org Md. Mudud Hassan Shovel Focal person, BRAC, mh.shovel@brac.net
2 | 21.2136 | 92.1568 |  | F | As same as above | As same as above | As same as above | As same as above | As same as above
3 | 21.2136 | 92.1566 |  | F | As same as above | As same as above | As same as above | As same as above | As same as above
4 | 21.2136 | 92.1566 |  | F | As same as above | As same as above | As same as above | As same as above | As same as above