| SL No | Work components as per RDPP (with quantity) | Qty | Unit | Estimated Cost | Achievement up to last FY June/2014 | Target of the current year | Progress up to the month of the current year |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Financial | Physical (%) of the component) | Financial | Physical (%) of the component) | Financial | Physical (%) of the component) |
| a) | Revenue component | - | - |
| 1 | Water quality test | LS |  | 2.00 | 2.00 | 100% | - | - | - | - |
| 2 | Human resource Development | LS |  | 0.60 | 0.50 | 83.33% | 0.10 | - | - | - |
| 3 | Supply and Services | LS |  | 34.40 | 25.00 | 72.67% | 9.00 | 26.16% | 9.00 | 26.16% |
|  | a) Sub-Total Revenue component |  |  | 37.00 | 27.50 | 74.32% | 9.00 | 26.16% | 9.00 | 26.16% |
| b) | Capital Component |
| 4 | Installation of test tube wells | 28 Nos | No | 12.04 | 9.91 | 92.86% | 1.38 | 7.14% | 1.14 | 7.14% |
| 5 | Installation of production tube wells & Electric connection | 14Nos | No | 160.58 | 130.66 | 85.71% | 29.92 | 14.29% | 26.40 | 14.29% |
| 6 | Pump House & Boundary wall | 14Nos | No | 56.00 | 48.00 | 85.71% | 8.00 | 14.29% | 8.00 | 14.29% |
| 7 | Pump & Motor purchase, Installation & Electric Connection | 14Nos | No | 117.60 | 83.23 | 85.71% | 34.37 | 14.29% | 34.37 | 14.29% |
| 8 | Water meter supply & Installation | 2100No | No | 84.00 | - | 0.00% | 63.07 | 100% | 56.34 | 100% |
| 9 | Pipe Line |  |  |  |  |  |  |  |  |  |
| 10 | 200mm dia pipe line | 3.5 KM | KM | 63.70 | 54.01 | 85.71% | 9.69 | 14.29% | 9.69 | 14.29% |
| 11 | 150mm dia pipe line | 14 KM | KM | 166.04 | 140.12 | 85.71% | 19.92 | 14.29% | 19.92 | 14.29% |
| 12 | 100mm dia pipe line | 64.19 KM | KM . | 507.10 | 206.36 | 65.43% | 214.50 | 34.57% | 213.892 | 34.57% |
| 13 | Construction of Surface drains | 12 KM | KM . | 270.00 | 270.00 | 100% | - | - | - | - |
| 14 | Dustbin | 30Nos | No | 6.00 | 6.00 | 100% | - | - | - | - |
| 15 | Public Toilet | 12Nos | No | 43.20 | 13.17 | 50% | 30.03 | 50% | 30.03 | 50.00% |
| 16 | Installation of Tara pump | 75Nos | No | 16.50 | 16.50 | 100% | - | - | - |  |
| 17 | House connection | 2100Nos | No | 126.00 | 23.05 | 33.90% | 68.02 | 66.10% | 67.00 | 66.10% |
| 18 | Purchase & Installation Auto Voltage Regulator | 14 Nos | No | 42.00 | 36.00 | 85.71% | 6.00 | 14.29% | 4.50 | 14.29% |
| 19 | O & M Equipment | LS | No | 17.50 | 15.00 | 85.71% | 2.50 | 14.29% | 2.50 | 14.29% |
| 20 | Pickup | 1 No | No | 50.00 | 46.89 | 100% | - | - | - | - |
| 21 | Computer with Printer & Other Accessories AcceAccessories | 7 No | No | 4.20 | 0.60 | 14.28% | 3.60 | 85.72% | 3.60 | 85.72% |
|  | b) Sub-Total Capital component |  |  | 1742.46 | 1099.50 | - | 491.00 | - | - | - |
|  | c) Physical Contingency |  |  | 0.19 | 0.00 |  | - |  |  |  |
|  | d) Price Contingency |  |  | 0.20 | 0.00 |  | - |  |  |  |
|  | Grand Total |  |  | 1779.85 | 1127.00 | - | 500.00 | - | 486.382 | - |

9. Reasons for the delay of Project implementation : Due to late approval of DPP, project could not start in time and on the other hand fund allocation was not as per DPP provision in FY’ 2010-11, 2011-12, 2012-13 & 2013-14 though project period was initially up to June/2012 and which is extended up to June/2015.

10. Existing problems of implementation of the project: N/A.

# Text boxes

8. Target Achievement of the Components of the Project

(Taka in Lakh)